## Slide 1: SD5953 Successful Project Management Work Breakdown Structure
School of Design
The Polytechnic University of Hong Kong

## Slide 2
IMPORTANT
Please sit with the members
of your final group project

## Slide 3
polyusd5953@gmail.com
Graham Leach, Instructor
www.graham-leach.com

## Slide 4: Work Breakdown Structure
Deconstructing and Organizing Atomic Tasks

## Slide 5: Wikipedia - Work Breakdown Structure
A Work Breakdown Structure (WBS) is a mapping of the deliverable-oriented elements of a project down to the smallest feasible component. The WBS is used to help group and link the elements that compose a project, to expose their underlying relations.
The WBS supports further Project Management refinment and development such as cost estimating, schedule development, task structuring, task sequencing and project control.
A WBS element may relate to a product, data or a service.
http://en.wikipedia.org/wiki/Work_breakdown_structure

## Slide 6: The Work Breakdown Structure
A WBS helps to decompose a project into a hierarchy of phases, deliverable networks and work packages. Ultimately, it is a tree-like structure that clearly shows the relationships and subdivisions of the inputs required to achieve the Scope.
A WBS is arrived upon by successively decomposing the project Scope into ever more specific and granular phases and steps.
Once a WBS Element cannot be decomposed any further, the WBS has arrived at the Work Package or ATOMIC Task level.
http://en.wikipedia.org/wiki/Work_breakdown_structure

## Slide 7: WBS Coding Schemes
It is common for a WBS element to have a systematic number.
This comes from the fact that the WBS was developed by a large, highly structured organization (DoD). The purpose of the numbering is to provide a consistent way to use a WBS across systems regardless of vendor or service. It also aids in recognizing WBS elements appearing in any written context.
http://en.wikipedia.org/wiki/Work_breakdown_structure

## Slide 8: Example Coding – A Bicycle BOM
http://en.wikipedia.org/wiki/Work_breakdown_structure
1.1.2 Handlebar identifies that item as a Level 3 element. This information is encoded, because its name is composed of three numbers separated by a decimal point, implying that there are two more levels of components.

## Slide 9: WBS Misconceptions
A WBS is NOT a complete project document. It acts more like a transitional document, and input to later stages of work. A WBS is not a Project Plan because:
It does not say WHO is to accomplish the tasks in the project.
It does not specify WHEN the tasks in the project are done.
http://en.wikipedia.org/wiki/Work_breakdown_structure

## Slide 10: HR Example - “Layers”
A HORIZONTAL view is the “Layers” of the Project

## Slide 11: HR Example – “Pillars”
A VERTICAL view is the “Pillars” of the Project

## Slide 12: WBS Element Attributes
Four attributes common to every WBS element are:
It directly relates to the Scope of the project.
It falls between the Start and End time of the project.
It is paid for from the Budget of the project.
It utilizes the Resources assigned to the project.
http://en.wikipedia.org/wiki/Work_breakdown_structure

## Slide 13: WBS Element “Sanity Checks”
80 Hour Rule: No single activity or group of activities to produce a single deliverable should be more than 80 hours of effort.
Single Reporting Period Rule: No activity or series of activities should be longer than a single reporting period. If the project team is reporting progress monthly, then no single activity or series of activities should be longer than one month long.
Common Sense Rule: If something looks or feels wrong while you are constructing the WBS, it probably is. Feel free to redo.
http://en.wikipedia.org/wiki/Work_breakdown_structure

## Slide 14: Is This Example A WBS?
DISCUSSION: Is this a proper WBS?

## Slide 15: Work Packages & ATOMIC Tasks
Getting Down to the Checklist

## Slide 16: A WBS Organizes Work Packages
Work Packages exist at the lowest management level of a project.
Work Packages are composed of at least one ATOMIC task, which is work that cannot be any further decomposed, and must be:
  In accordance with the WBS “Sanity Checks”
  Capable of producing a measurable deliverable
  Able to be realistically and confidently estimated
http://en.wikipedia.org/wiki/Work_breakdown_structure

## Slide 17: Where Work Packages Go in a WBS

## Slide 18: YouTube – WBS Tutorials
242 - Versatile Company (4 min)
  http://www.youtube.com/watch?v=6oEMEo7sRy0
243 - SimonSez (16 min)
  http://www.youtube.com/watch?v=wPAoikQ5k-s

## Slide 19: Questions?

## Slide 20: Thank You